## Sheet1
Name | Start | Finish | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project Proposal Document | Week 1 | Week 2 | 1 week
Golang Simple HTTP Client/Server | Week 2 | Week 3 | 1 week
Computer Networks research | Week 1 | Week 4 | 3 weeks
Requirements Specification Document (Initial) | Week 3 | Week 5 | 2 weeks
Golang research | Week 1 | Week 5 | 4 weeks
TCP Header | Week 5 | Week 7 | 2 weeks
Sockets | Week 6 | Week 8 | 2 weeks
Software Development Plan Document (Initial) | Week 7 | Week 9 | 2 weeks
Encoding/Decoding | Week 6 | Week 10 | 4 weeks
Software Development Plan Document (Updated) | Week 9 | Week 11 | 2 weeks
3-way handshake | Week 9 | Week 12 | 3 weeks
Basic Message | Week 11 | Week 12 | 1 week
Requirements Specification Document (re-submit) | Week 11 | Week 13 | 2 weeks
Send a file | Week 11 | Week 13 | 2 weeks
Multiple clients | Week 11 | Week 15 | 4 weeks
Bugs/Errors | Week 2 | Week 16 | 14 weeks
Project Delivery | Week 1 | Week 17 | 17 weeks
Project Presentation | Week 15 | Week 17 | 2.5 weeks
SCRUMS | Week 1 | Week 16 | Ongoing
Written Status Reports | Week 1 | Week 16 | Ongoing